## Programme Architecture
Month | October 2021 |  |  | November 2021 |  |  |  | December 2021 |  | January 2022 |  |  | 2021-02-01 |  |  | 2021-03-01 |  |  | 2021-04-01 |  | 2021-05-01
Calendar Week | CW40 |  |  | CW44 |  |  |  | CW48 |  | CW01 |  |  | KW5 |  |  | KW9 |  |  | KW14 |  | KW18
Phase | PHASE II | [14 empty] | EVOLVE
Evaluation | [11 empty] | FINAL EVENT and Evaluation of PHASE 2 |  |  | Evaluation for EVOLVE phase: based on pitches and KPIs & executed by jury: ?
Business Training | [8 empty] | Individual Mentoring sessions: Business Mentoring session.-- Date to be agreed on each case with the mentor - team |  |  |  | Webinar 10: "Sales" by Patrick Majunke (ESH), 04 February 2020, 11am CEST (CONFIRMED by André) | Webinar 11: Public Funding focused on SMEs (Sara Mateo, Zabala) - 11 February 2021, 12pm (CONFIRMED), timing? |  |  | Webinar 12: Frequently Asked Questions about pitching to investors and win their trust and money (Murli B.), 11/03/2021, 12 CET | Individual Mentoring Session with Murli | Webinar 13: Marketing & Communications by Lena Vattrodt and Lara Barnini (ESH), 23/03/2020, 10 am (CONFIRMED by André) | Webinar 14: Investor relations (eSH) - TBC
Technical Training |  | Linked Data (NGSI-LD): describes the evolution of NGSI v2 specitication to manage linked data: NGSI-LD (based on JSON-LD) (Oct 14th, 10 AM) | IDRA - Open Data Federation Platform: web application able to federate existing Open Data Management Systems (ODMS) based on different technologies providing a unique access point to search and discover open datasets coming from heterogeneous sources (Oct 27th) |  | 1. VoCol: a collaborative ontology development tool - by Khiat, Abderrahmane | 2. OpenSource business models (Nov 17th) | Data privacy and GDPR vocabularies and ontologies - by Mousavinezhad, Najmehsadat | [7 empty] | 20/02/2020 - Plenary Meeting, Bilbao | [6 empty] | Pleanary Meeting + 2nd Period Review Meeting: 14/05/2020
Infrastructure and Tools Training |  | Linked Data
Optional Training | [10 empty] | Webinar Public funding Opportunities in Horizon Europe (Jan 13th, 10 AM)
Payments to teams | [11 empty] | Final Payment (% depending on KPIs completion) |  |  |  | 15000

## Assistance_Business_Trainings (hidden)
Third Partie | Path to Product Market fit, The Basics (22 Sept) | Homework completed | Finding Problem. Solution Fit (6 Oct) | Homework completed | Path to Product Market fit, knowing the job (20 Oct) | Homework completed | Experimentation and reducing risk (2 Nov) | Homework completed | Blue Ocean Strategy and Networking hacks (10 Nov) | Homework completed | Business Mentoring session (18 Nov) | Homework completed | Business Mentoring session (09 Dec) | Homework completed | Company name | Survey
DIP | y | y | y | y | y | y | y |  | y | y | y | no homework |  |  | OwnYourData | x | Christoph Fabianek
OpenXPort | y | y | y | y | y | y | y | y | y | y | y |  |  |  | audriga | x | Hans-Jörg Happel
IDAVEV-P2P | y | y | y | y | y | y | y |  |  | y | y |  |  |  | University of Alcalá | x | Miguel-Angel Sicilia
ALIAS | y | y | y | y | y | y | y | y | y | y | y |  |  |  | ALIAS IDENTITY | x | Mehdi medjaoui
DPella | y | y | y | y | y | y | y | y | y | y | y |  |  |  | DPella | x | Carola Compá
Domi | y | y | y | y | y | y | y | y |  | y | y |  |  |  | Domi (Domi Labs) | x | Katrie Lowe
ORATORIO | y | y | y | y | y | y | y | y | y | y | y |  |  |  | GridPocket SAS |  | GLUSZAK Filip
UI-Transfer | y | y | y | y | y | y | y | y | y | y | y |  |  |  | Digita BV | x | Tom Haegemans
Checkpipe Charlie | y | y | y | y | y | y | y | y | y | y | y |  |  |  | Dain Studios OY | x | Arttu Huhtiniemi
Open PKG | y | y | y | y | y | y | y | y | y | y | y |  |  |  | Trace Labs - OriginTrail Core Developers | x | Jurij Škornik
Prov4ITData | y | y | y | y | y | y | y | y | y | y | y |  |  |  | Ben De Meester | x | De Meester, Ben

## Assistance_Technical_Trainings (hidden)
Third Partie | Introduction to GDPR & data subject’s rights (16 Nov) | Linked data & semantic web technologies (23 Nov) | Data sovereignty (25 Nov)
DIP | y | y | y | The training did not have any homework. We had interactive sessions, and the teams participated in a few exercises. Most of them were engaged, but I don’t remember much who was active in the session and who was not.
OpenXPort | y | y | y
IDAVEV-P2P | y | y | y
ALIAS | y | y | y
DPella | y | y | y
Domi | y | y | y
ORATORIO | y | y | y
UI-Transfer | no | y | y
Checkpipe Charlie | y | y | y
Open PKG | y | y | y
Prov4ITData | y | y | y

## Assistance_Infrastructure (hidden)
Third Partie | Application Infrastructire Webinar (2 Oct) | Support Tool Training (2 Oct)
DIP
OpenXPort
IDAVEV-P2P
ALIAS
DPella
Domi
ORATORIO
UI-Transfer
Checkpipe Charlie
Open PKG
Prov4ITData

## Hoja1 (hidden)
Attendance | Deliverable | Attendance | Deliverable | Attendance | Deliverable | Attendance | Deliverable | Attendance | Deliverable | Attendance | Deliverable | Attendance | Deliverable
Collective Training: Path to Product Market fit, The Basics.-- 22 September |  | Collective Training: Finding Problem. Solution Fit.-- 6 October |  | Individual call with the mentor assigned to each project. Around 15 October |  | Collective Training: Path to Product Market fit, knowing the job.-- 20 October |  | Collective Training: Experimentation and reducing risk.-- 3 November |  | Collective Training:Blue Ocean Strategy and Networking hacks.-- 10 November |  | Individual Mentoring sessions: Business Mentoring session.-- 18 November
5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5%
10% |  | 10% |  | 10% |  | 10% |  | 10% |  | 10% |  | 10%
Attendance |  | Attendance |  | Attendance
Collective Training: An introduction to GDPR & data subject’s rights.-- 16 November |  | Collective Training: Linked data & semantic web technologies.-- 23 November |  | Data sovereignty. -25 November |  |  |  | Total | 100%
10% |  | 10% |  | 10%