## Workplan
Serial	Task	Description	Subtask milestone	Cost %	Cost €
1	Specification and documentation	JSON Schema for F3 are published in a dedicated repository	* Commits merged in the https://lab.forgefriends.org/friendlyforgeformat/f3-publisher repository / * A formatted online version of the documentation at https://f3.forgefriends.org	4,00 %	2002
2	Documentation of the F3 lifecycle	* Guide for newcomers / * Roadmap / * Low hanging fruits / * Reference for specification developers	* A repository with the documentation at https://lab.forgefriends.org/friendlyforgeformat/f3-guide repository / * A formatted online version of the documentation at https://f3.forgefriends.org	4,00 %	2003
3	Go reference implementation: user	Internal representation of a user, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2005
4	Go reference implementation: project	Internal representation of a project, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2007
5	Go reference implementation: issue	Internal representation of a issue, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2011
6	Go reference implementation: label	Internal representation of a label, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2013
7	Go reference implementation: milestone	Internal representation of a milestone, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2017
8	Go reference implementation: release	Internal representation of a release, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2019
9	Go reference implementation: asset	Internal representation of a asset, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2023
10	Go reference implementation: pull request	Internal representation of a pull request, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2029
11	Go reference implementation: repository	Internal representation of a repository, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2031
12	Go reference implementation: comment	Internal representation of a comment, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2037
13	Go reference implementation: reaction	Internal representation of a reaction, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2041
14	Go reference implementation: review	Internal representation of a review, export / import functions for F3, Gitea via an API, Gitea via the internals.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2043
15	Go reference implementation: identifiers	Internal representation of a object identifiers, export / import functions for F3, Gitea via an API, Gitea via the internals. They need to be remapped when mirroring an object from one forge to another.	* A commit in https://lab.forgefriends.org/friendlyforgeformat/gof3	4,00 %	2047
16	Integration in the Gitea codebase	The F3 Go reference implementation is used as an alternative for the internal format used for repositories dump and restore features in the Gitea codebase.	* A pull request merged in https://lab.forgefriends.org/forgefriends/forgefriends/ or https://github.com/go-gitea/gitea	4,00 %	2053
17	User Research: question	A research project question briefly outlines the question to explore in the research project. It is helpful to start the research project by writing a research project question. / What are the goals of the research project? What do we need to learn more about? Who are the personaes that are primarily concerned by F3?	* A commit at https://lab.forgefriends.org/friendlyforgeformat/f3-ux including the research question as well as the definition of the personae relevant to F3	4,00 %	2059
18	User Research: recruit participants	Write down interview scripts for each personae. Recruit ten participants willing to be interviewed.	* A commit at https://lab.forgefriends.org/friendlyforgeformat/f3-ux including the interview scripts	4,00 %	2061
19	User Research: interviews & transcriptions	Each participant to the User Research is interviewed and recorded. The recording is transcribed for later analysis.	* The recording of the interviews in commits at https://lab.forgefriends.org/friendlyforgeformat/f3-ux (if the participant gave their consent) / * The anonymized transcript of the interview in commits at https://lab.forgefriends.org/friendlyforgeformat/f3-ux (if the participant gave their consent)	4,00 %	2067
20	User Research: affinity mapping session	Organize a live affinity mapping session https://www.nngroup.com/articles/affinity-diagram/ with six participants to analyse the transcripts of the interviews.	* A video recording of the affinity mapping session at https://lab.forgefriends.org/friendlyforgeformat/f3-ux	4,00 %	2071
21	User Research: report	Analyze the result of the affinity mapping session and the interviews. Write down a report that concludes with emerging themes and recommendations explaining why F3 should focus.	* A user research report at https://lab.forgefriends.org/friendlyforgeformat/f3-ux	4,00 %	2073
22	First release	The first F3 release is a bundle that includes: / * The specifications and documentation / * The Go reference implementation / They are verified to be consistent and tagged with the same version number.	simultaneous publication of F3 version 1.0.0 at: / * https://readthedocs.org/ for the specifications / * https://pkg.go.dev/ for the Go reference implementation	4,00 %	2079
23	Reach out to standard bodies	Reach out to OASIS and propose F3 as a new standard	* A submitted application acknowledged as received by OASIS	4,00 %	2083
24	Diversity	Improving the gender and linguistic diversity is an ongoing challenge for every Free Software project, F3 included. It must be addressed by concrete actions to improve the situation.	* Translation of the diversity guidebook https://wiki.chatons.org/doku.php/heberger/inclusivite / * New repository dedicated to the diversity guidebook / * Merged pull requests to the diversity guidebook	4,00 %	2089
25	Reporting & Videoconferences	Monthly report published on https://forgefriends.org/ with detailed information about the work done regarding federation since the last report, including links where it can be audited. Organize a monthly public, online, meeting to discuss the monthly report. The videoconference is open to the general public and recorded.	* Monthly reports published on https://forgefriends.org / * Recordings of the videoconferences	4,00 %	2097

## Data
Amount		Primes
50000		1	2
Remains		2	3
-1060		3	5
		4	7
		5	11
		6	13
		7	17
		8	19
		9	23
		10	29
		11	31
		12	37
		13	41
		14	43
		15	47
		16	53
		17	59
		18	61
		19	67
		20	71
		21	73
		22	79
		23	83
		24	89
		25	97